## Sheet1
TEACH AND LEARN Gantt Chart
Rajat,Nidhi,Mayur,Mishan and Preet
| Time alloted | Managed by | Starting Date
TASKS |  |  |  | TASKS | START DATE | Days to complete
Analysis |  |  |  | Analysis | 2017-12-28 | 17
Requirement Gathering data | 3 days | whole team | 2017-12-28 | Management | 2018-01-15 | 12
Technical specification | 2 days | mayur,mishan | 2018-01-02 | Design | 2018-01-30 | 23
Estimated time | 2 days | whole team | 2018-01-04 | Implementation | 2018-02-05 | 28
Documentation (report) | 3 days | Rajat,Nidhi,Preet | 2018-01-06 | Testing | 2018-03-22 | 12
Estimated cost | 2 days | whole team | 2018-01-09
Identifying team specialities | 2 days | whole team | 2018-01-11
Management
Distributing workload | 3 days | whole team | 2018-01-15
Fetching resources over the net | 4 days | preet nidhi | 2018-01-18
References | 3 days | preet nidhi | 2018-01-22
Prerequisites Management | 2 days | whole team | 2018-01-25
Managing Softwares | 1 day | Rajat Mayur | 2018-01-27
Additional Prints/doc management | all time | Preet and nidhi | all time
Design
Sample Process Design | 2 days | Rajat Mayur | 2018-01-30
Workflow (flowcharts) | 2-3 days | Rajat Mayur | 2018-02-01
UML Design | 5 days | Mishan Preet Nidhi | 2018-02-04
GUI Design | 5 days | Mishan Preet Nidhi | 2018-02-21
Implementation
Coding | 15-18 days | Rajat Mayur | 2018-02-05
Error-solving | 10 days | Whole team… | 2018-03-05
Immediate Help support | always for implementation | Preet and Nidhi | all time
Testing
Unit testing for bugs | 5 days | Whole team | 2018-03-22
Bug Updates that are identified | 7-8 days | Rajat Mayur if code bug issue | 2018-03-28
Testing on changes performed | 4 days | Mishan nidhi preet if gui bug issue | 2018-03-28